## Hoja 1
| USERSTORY | TASKS | AREA | PRIORITY | STATUS | RESPONSIBLE | TOTAL HOURS | START DAY | END DAY | COMMENTS | FILE NAME
A | Logo Roll
A |  | Mus_Logo_Ver1.wav | Música | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Mus_Logo_Ver1.wav
B | Pantalla de Inicio
B |  | Mus_Menu_Ver1.wav | Música | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Mus_Menu_Ver1.wav
B |  | Stp_Forest_Ver1.wav | Sfxs | B | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Forest_Ver1.wav
B |  | Amb_Leaves_Ver1.wav | Sfxs | B | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Leaves_Ver1.wav
B |  | UI_PreSelect_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreSelect_Ver1.wav
B |  | UI_Select_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Select_Ver1.wav
B |  | UI_PreOpen_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreOpen_Ver1.wav
B |  | UI_Open_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Open_Ver1.wav
B |  | UI_PreClose_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreClose_Ver1.wav
B |  | UI_Close_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Close_Ver1.wav
B |  | UI_PreExit_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreExit_Ver1.wav
B |  | UI_Exit_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Exit_Ver1.wav
B |  | Imp_Dusk_Ver1.wav | Sfxs | B | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Imp_Dusk_Ver1.wav
C | Transición 1 (Pantalla Negra)
C |  | Mus_killer_Ver1.wav | Música | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Mus_killer_Ver1.wav
C |  | Amb_Fountain_Ver1.wav | Sfxs | B | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Fountain_Ver1.wav
D | Escena 1 Townsquare de dia (Escena del crimen 1)
D |  | Mus_killer_Ver1.wav | Música | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Mus_killer_Ver1.wav
D |  | UI_PrePage_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PrePage_Ver1.wav
D |  | UI_Page_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Page_Ver1.wav
D |  | Sfxs_Police_Ver1.wav | Sfxs | B | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Police_Ver1.wav
D |  | Sfxs_Splat_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Splat_Ver1.wav
D |  | Sfxs_laughs_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_laughs_Ver1.wav
D |  | Stp_Townsquare_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Townsquare_Ver1.wav
E | Transición: Tomatez
E |  | Sfxs_Splat_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Splat_Ver1.wav
F | Escena 1.1 Jessie House
F |  | Mus_house_Ver1.wav | Música | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Mus_house_Ver1.wav
F |  | UI_PrePage_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PrePage_Ver1.wav
F |  | UI_Page_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Page_Ver1.wav
F |  | Stp_Townsquare_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Townsquare_Ver1.wav
F |  | Amb_Leaves_Ver1.wav | Sfxs | B | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Leaves_Ver1.wav
|  | UI_PrePositive_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PrePositive_Ver1.wav
|  | UI_Positive_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Positive_Ver1.wav
|  | UI_PreNegative_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreNegative_Ver1.wav
|  | UI_Negative_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Negative_Ver1.wav
F |  | Sfxs_Bingo_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Bingo_Ver1.wav
E | Transición 2 (Pantalla Negra)
E |  | Amb_Wind_Ver1.wav | Sfxs | B | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Wind_Ver1.wav
E |  | Sfxs_Whispering_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Whispering_Ver1.wav
F | Escena 1.2 Jessie House
F |  | Mus_house_Ver1.wav | Música | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Mus_house_Ver1.wav
|  | UI_PrePage_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PrePage_Ver1.wav
F |  | UI_Page_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Page_Ver1.wav
F |  | Sfxs_Bite_Ver1.wav | Sfxs | D | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Bite_Ver1.wav
F |  | Sfxs_Pet_Ver1.wav | Sfxs | D | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Pet_Ver1.wav
F |  | Sfxs_Snugle_Ver1.wav | Sfxs | D | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Snugle_Ver1.wav
F |  | Sfxs_Hat_Ver1.wav | Sfxs | c | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Hat_Ver1.wav
|  | UI_PreSelect_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreSelect_Ver1.wav
F |  | UI_Select_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Select_Ver1.wav
F |  | Sfxs_Brush_Ver1.wav | Sfxs | D | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Brush_Ver1.wav
F |  | Sfxs_Screech_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Screech_Ver1.wav
|  | UI_PreMirella_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreMirella_Ver1.wav
F |  | UI_Mirella_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Mirella_Ver1.wav
|  | UI_PreGus_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreGus_Ver1.wav
F |  | UI_Gus_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Gus_Ver1.wav
G | Transición 3.1 Mirella
G |  | Amb_Fountain_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Fountain_Ver1.wav
G |  | Stp_Townsquare_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Townsquare_Ver1.wav
H | Escena 3.1 Mirella Boutique
H |  | Mus_Boutique_Ver1.wav | Música | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Mus_Boutique_Ver1.wav
H |  | Sfxs_Boutique_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Boutique_Ver1.wav
H |  | Stp_Boutique_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Boutique_Ver1.wav
H |  | Sfxs_Screech_Ver1.wav | Sfxs | B | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Screech_Ver1.wav
|  | UI_PrePositive_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PrePositive_Ver1.wav
H |  | UI_Positive_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Positive_Ver1.wav
|  | UI_PreNegative_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreNegative_Ver1.wav
H |  | UI_Negative_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Negative_Ver1.wav
H |  | Stp_Boutique_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Boutique_Ver1.wav
H |  | UI_Precoat_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_Precoat_Ver1.wav
H |  | UI_Coat_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Coat_Ver1.wav
|  | UI_PrePicture_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PrePicture_Ver1.wav
H |  | UI_Picture_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Picture_Ver1.wav
|  | UI_Preground_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_Preground_Ver1.wav
H |  | UI_Ground_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Ground_Ver1.wav
H |  | Sfxs_Unplesant_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Unplesant_Ver1.wav
|  | Stp_Boutique_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Boutique_Ver1.wav
H |  | Stp_Backstore_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Backstore_Ver1.wav
H |  | Stp_Boutique_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Boutique_Ver1.wav
H |  | Sfxs_Folks_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Folks_Ver1.wav
|  | Sfxs_flaping_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_flaping_Ver1.wav
H |  | Sfxs_bag_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_bag_Ver1.wav
H |  | Stp_Boutique_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Boutique_Ver1.wav
H |  | Sfxs_Dress_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Dress_Ver1.wav
H |  | Sfxs_paper_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_paper_Ver1.wav
H |  | Sfxs_Boutique_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Boutique_Ver1.wav
H |  | Sfxs_bag_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_bag_Ver1.wav
|  | UI_PreMirella_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreMirella_Ver1.wav
H |  | UI_Mirella_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Mirella_Ver1.wav
|  | UI_PreGus_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreGus_Ver1.wav
H |  | UI_Gus_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Gus_Ver1.wav
|  | UI_PreCase_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreCase_Ver1.wav
H |  | UI_Case_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Case_Ver1.wav
I | Transición 3.2 To Gus Cabin
I |  | Amb_Branches_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Branches_Ver1.wav
I |  | Stp_Forest_Ver1.wav | Sfxs | B | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Stp_Forest_Ver1.wav
J | Escena 3.2 Gus Cabin
J |  | Amb_Cracking_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Cracking_Ver1.wav
|  | Sfxs_Fly_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_fly_Ver1.wav
J |  | Sfxs_creaking_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_creaking_Ver1.wav
|  | UI_PreCloset_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreCloset_Ver1.wav
J |  | UI_Closet_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Closet_Ver1.wav
J |  | Sfxs_Metalic_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Metalic_Ver1.wav
J |  | Sfxs_axe_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_axe_Ver1.wav
|  | UI_PreRoom_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreRoom_Ver1.wav
J |  | UI_Room_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Room_Ver1.wav
|  | UI_PrePositive_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PrePositive_Ver1.wav
|  | UI_Positive_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Positive_Ver1.wav
|  | UI_PreNegative_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreNegative_Ver1.wav
|  | UI_Negative_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Negative_Ver1.wav
J |  | Sfxs_Chair_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Chair_Ver1.wav
J |  | Sfxs_flies_Ver1wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_flies_Ver1wav
J |  | Sfxs_write_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_write_Ver1.wav
J |  | Sfxs_paper_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_paper_Ver1.wav
J |  | Amb_Chill_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Chill_Ver1.wav
J |  | Sfxs_weird_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_weird_Ver1.wav
J |  | Sfxs_match_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_match_Ver1.wav
J |  | Sfxs_Tree_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_tree_Ver1.wav
J |  | Sfxs_Screech_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Screech_Ver1.wav
J |  | Sfxs_weird_Ver1.wav |  |  | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_weird_Ver1.wav
J |  | Sfxs_closing_Ver1.wav |  |  | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_closing_Ver1.wav
J |  | Sfxs_flaping_Ver1.wav |  |  | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_flaping_Ver1.wav
|  | UI_PreMirella_Ver1.wav |  | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreMirella_Ver1.wav
J |  | UI_Mirella_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Mirella_Ver1.wav
|  | UI_PreGus_Ver1.wav |  | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreGus_Ver1.wav
J |  | UI_Gus_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Gus_Ver1.wav
|  | UI_PreCase_Ver1.wav |  | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreCase_Ver1.wav
J |  | UI_Case_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | UI_Case_Ver1.wav
K | Transición 4 To Townsquare night
K |  | Amb_Rain_Ver1.wav | Sfxs | C | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Rain_Ver1.wav
L | Escena 4 Townsquare Night
L |  | Mus_killer_Ver1.wav | Música | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 | loop | Mus_killer_Ver1.wav
L |  | Amb_Rain_Ver1.wav | Sfxs | C | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Rain_Ver1.wav
L |  | Sfxs_logs_Ver1.wav | Sfxs | C | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_logs_Ver1.wav
|  | SFxs_murmurs_Ver1.wav | Sfxs | B | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | SFxs_murmurs_Ver1.wav
|  | UI_PreMirella_Ver1.wav |  | C | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreMirella_Ver1.wav
L |  | UI_Mirella_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | UI_Mirella_Ver1.wav
|  | UI_PreGus_Ver1.wav |  | C | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreGus_Ver1.wav
L |  | UI_Gus_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | UI_Gus_Ver1.wav
|  | UI_PreSomething_Ver1.wav |  |  | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreSomething_Ver1.wav
L |  | UI_Something_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | UI_Something_Ver1.wav
|  | UI_PreNothing_Ver1.wav |  |  | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 | loop | UI_PreNothing_Ver1.wav
L |  | UI_Nothing_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | UI_Nothing_Ver1.wav
M | Transición 4.1 townsquare acuseation Mirella
L |  | Imp_First_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Imp_First_Ver1.wav
L |  | Imp_Second_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Imp_Second_Ver1.wav
L |  | Imp_Third_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Imp_Third_Ver1.wav
M | Transición 4.1.1 To Mirella boutique
M |  | Stp_Running_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Stp_Running_Ver1.wav
M |  | Sfxs_angry_Ver1.wav | Sfxs | B | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_angry_Ver1.wav
N | Transición 4.1.2 From Mirella boutique
N |  | Sfxs_angry_Ver1.wav | Sfxs | B | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_angry_Ver1.wav
N |  | Sfxs_gasoline_Ver1.wav | Sfxs | B | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_gasoline_Ver1.wav
O | Transición 4.1.3 After Mirella Murder
O |  | Sfxs_Unplesant_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Unplesant_Ver1.wav
K | Transición 4.2 townsquare acuseation Gus
L |  | Imp_Second_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Imp_Second_Ver1.wav
L |  | Imp_Third_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Imp_Third_Ver1.wav
M | Transición 4.2 To Gus Cabin
D |  | Sfxs_angry_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_angry_Ver1.wav
N | Transición 4.2.1 From Mirella boutique
N |  | Sfxs_angry_Ver1.wav |  |  | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_angry_Ver1.wav
N |  | Sfxs_gasoline_Ver1.wav | Sfxs |  | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_gasoline_Ver1.wav
O | Transición 4.2.3 After Mirella Murder
O |  | Sfxs_Unplesant_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Unplesant_Ver1.wav
P | Transición 4.3 townsquare acuseation other thing
P |  | Imp_Second_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Imp_Second_Ver1.wav
P |  | Imp_Third_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Imp_Third_Ver1.wav
Q | Transición 4.3.1 To the forest
Q |  | Stp_Running_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Stp_Running_Ver1.wav
Q |  | Sfxs_angry_Ver1.wav |  | B | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_angry_Ver1.wav
R | Transición 4.3.2 in Jessie Room
R |  | Mus_Dusk_Ver1.wav | Música | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 | loop | Mus_Dusk_Ver1.wav
R |  | Amb_Branches_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 | loop | Amb_Branches_Ver1.wav
R |  | Sfxs_Slam_Ver1.wav | Sfxs | A | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Slam_Ver1.wav
R |  | Sfxs_Laugh_Ver1.wav | Sfxs | B | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Laugh_Ver1.wav
R |  | Sfxs_Digin_Ver1.wav | Sfxs | C | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Digin_Ver1.wav
R |  | Sfxs_Trap_Ver1.wav | Sfxs | C | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Trap_Ver1.wav
R |  | Sfxs_Hearth_Ver1.wav | Sfxs | C | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 | loop | Sfxs_Hearth_Ver1.wav
R |  | Sfxs_Desintegret_Ver1.wav | Sfxs | C | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Desintegret_Ver1.wav
R |  | Sfxs_Hoot_Ver1.wav | Sfxs | C | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Hoot_Ver1.wav
R |  | Imp_Dusk_Ver1.wav | Sfxs | B | Completed | Oz | 40hrs | 2024-09-02 | 2024-09-25 |  | Imp_Dusk_Ver1.wav
S | Transición 4.4 townsquare acuseation no one
T | Transición 4.4.1 In Squaretown
T |  | Sfxs_angry_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_angry_Ver1.wav
T |  | Sfxs_gasoline_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_gasoline_Ver1.wav
T |  | Sfxs_Burning_Ver1.wav | Sfxs | C | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Burning_Ver1.wav
U | Transición 4.4.2 After Mirella Murder
U |  | Sfxs_Unplesant_Ver1.wav | Sfxs | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Sfxs_Unplesant_Ver1.wav
A | Credit Roll
A |  | Mus_Credits_Ver1.wav | Música | A | Completed | Oz | 50hrs | 2024-09-02 | 2024-09-25 |  | Mus_Credits_Ver1.wav